## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-02-05 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | First enemy and tower models imported |  | 80% | Possible Delays |  | 2022-02-05
|  |  |  | Towers shooting enemies |  | 30% | Possible Delays |  | 2022-02-12
|  |  |  | Tower building menu functionality |  | 50% | On Track |  | 2022-02-12
|  |  |  | Basic economy with enemies dropping coins |  | 0% | Future Task |  | 2022-02-12
|  |  |  | Swarm spawning |  | 30% | On Track |  | 2022-02-12
|  |  |  | Enemies taking damage |  | 0% | Possible Delays |  | 2022-02-12
|  |  |  | Ground tile models |  | 40% | On Track |  | 2022-02-12
|  |  |  | Another tower model |  | 0% | Future Task |  | 2022-02-19
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Reworked map created with nodes for turrets. Two types of enemies modeled and animated and one tower modeled and imported. Basic tower building menu. Mesh for dynamic pathfinding. Script to track score and money. Super basic enemy pathfinding. |  |  | Still importing enemy models and their animations. We were too ambitious about some of the tasks as well so their dates have been pushed back simply because the original dates would've required us to put in more time this week than we did. |  |  | We need to implement swarm spawning, tower attacking, enemies taking damage, and need to import our models and animations.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 9 | Risk | Towers shooting enemies might take more time than anticipated, especially if we add effects to it.
Peter Seely | AI Specialist/Enemy AI | 4.5
Nate Roylance | Chief Architect/Start Menu UI | 6
Joel Battaglia | Game Artist/Asset Creation | 3 | Issue
Joseph Scholl | Tower Expert/Tower Research | 5.3
Total |  | 27.8

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task