## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-01-29 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | First enemy and tower models imported |  | 70% | On Track |  | 2022-02-05
|  |  |  | Tower building menu |  | 30% | Possible Delays |  | 2022-02-05
|  |  |  | Towers shooting enemies |  | 0% | Future Task |  | 2022-02-05
|  |  |  | Basic economy with enemies dropping coins |  | 0% | Future Task |  | 2022-02-12
|  |  |  | Swarm spawning |  | 0% | Future Task |  | 2022-02-12
|  |  |  | Enemies taking damage |  | 0% | Future Task |  | 2022-02-05
|  |  |  | Enemy pathfinding |  | 30% | Possible Delays |  | 2022-02-05
|  |  |  | Another tower model |  | 0% | Future Task |  | 2022-02-19
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Github and Unity setup complete with all team members successfully working on the project. Basic Start Menu Created. Map created with nodes for turrets. Two types of enemies modeled and animated and one tower modeled. |  |  | Only research has been done for the tower building menu and the enemy pathfinding. |  |  | We now need to implement the mechanics to build towers and the mechanics for enemies to attack the base. Then, we need to implement towers shooting enemies.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 8 | Risk | Getting assets imported from blender into unity might take additional time since that requires a significant amount of work. Pathfinding might also be difficult since it will likely need to be calculated dynamically through code.
Peter Seely | AI Specialist/Enemy AI | 6.5
Nate Roylance | Chief Architect/Start Menu UI | 5
Joel Battaglia | Game Artist/Asset Creation | 8 | Issue
Joseph Scholl | Tower Expert/Tower Research | 6
Total |  | 33.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task