## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-03-12 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | Standardize codebase |  | 50% | On Track |  | 2022-03-19
|  |  |  | Tower change targetting code |  | 40% | On Track |  | 2022-03-26
|  |  |  | Tower change targetting UI |  | 50% | Possible Delays |  | 2022-03-19
|  |  |  | Import improved ground assets |  | 80% | Possible Delays |  | 2022-03-19
|  |  |  | Tower Upgrade Code |  | 0% | Future Task |  | 2022-03-26
|  |  |  | Tower Upgrade Assets |  | 0% | Future Task |  | 2022-03-26
|  |  |  | Tower Upgrade UI |  | 0% | Future Task |  | 2022-03-26
|  |  |  | Sound Effects |  | 0% | Future Task |  | 2022-04-02
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Enemies spawing and navigating towards base. Enemy health bars appearing and reflect level of health. Health bars animating when damage is taken. New floor tiles in game. |  |  | Updates to floor tiles have been delayed because Joel is currently taking a well-earned paternity leave. Some items have been postponed since they aren't necessary and other features need to be improved before new ones can be created. |  |  | Future tasks include implementing tower upgrades, new enemies, sound effects, and one shot player powers. Currently, the tasks are focused on improving the code base and giving the player more flexibility with their towers.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 4 | Risk | A current risk we face is moving too fast without resolving technical debt or standardizing naming conventions and code style. We are all so excited about current progress and new features that it may be easy to overlook the value of refactoring features that work already.
Peter Seely | AI Specialist/Enemy AI | 5
Nate Roylance | Chief Architect/Start Menu UI | 3
Joel Battaglia | Game Artist/Asset Creation | 0 | Issue | Technical problems with the integration of various technologies (Unity, Github, Blender, etc). Slowly being resolved as we learn how to better configure them for increased interoperability.
Joseph Scholl | Tower Expert/Tower Research | 1
Total |  | 13

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task