## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-03-05 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | Swarm spawning |  | 100% | Complete |  | 2022-02-19
|  |  |  | New floor tiles |  | 99% | Possible Delays |  | 2022-02-26
|  |  |  | Attack code for 2 new tower models |  | 90% | Possible Delays |  | 2022-02-26
|  |  |  | Health bars for enemies |  | 100% | Complete |  | 2022-03-12
|  |  |  | Upgrade/Destroy Towers |  | 50% | On Track |  | 2022-03-12
|  |  |  | Game Instructions |  | 50% | On Track |  | 2022-03-12
|  |  |  | Themed bgs |  | 0% | Future Task |  | 2022-03-12
|  |  |  | Player powers |  | 0% | Possible Delays |  | 2022-03-12
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Enemies spawing and navigating towards base. Enemy health bars appearing and reflect level of health. Health bars animating when damage is taken. New floor tiles in game. |  |  | Everyone needs to push their github branches and get them merged together. Updates to floor tiles have been delayed because Joel is currently taking a well-earned paternity leave. |  |  | New tower types are the two biggest tasks to be completed. They have both been delayed due to some unity issues. Then, we can begin to add sound effects, themed backgrounds, and game instructions.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 3.5 | Risk | A current risk we face is moving too fast without resolving technical debt or standardizing naming conventions and code style. We are all so excited about current progress and new features that it may be easy to overlook the value of refactoring features that work already.
Peter Seely | AI Specialist/Enemy AI | 5.5
Nate Roylance | Chief Architect/Start Menu UI | 4
Joel Battaglia | Game Artist/Asset Creation | 0 | Issue | Technical problems with the integration of various technologies (Unity, Github, Blender, etc). Slowly being resolved as we learn how to better configure them for increased interoperability.
Joseph Scholl | Tower Expert/Tower Research | 3
Total |  | 16

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task