## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-12-05 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | First enemy and tower models imported |  | 80% | Delayed |  | 2022-02-19
|  |  |  | Towers shooting enemies |  | 70% | On Track |  | 2022-02-19
|  |  |  | Ground tile models |  | 40% | On Track |  | 2022-02-19
|  |  |  | Basic economy with enemies dropping coins |  | 0% | Future Task |  | 2022-02-12
|  |  |  | Swarm spawning |  | 40% | Possible Delays |  | 2022-02-19
|  |  |  | Another tower model |  | 50% | On Track |  | 2022-02-19
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Reworked map created with nodes for turrets. Two types of enemies modeled and animated and one tower modeled and imported. Basic tower building menu. Mesh for dynamic pathfinding. Script to track score and money. Super basic enemy pathfinding. Economy created and working. Enemies taking damage. |  |  | Still importing enemy models and their animations since time has been spent created new models rather than importing them. |  |  | Main tasks are to implement swarm spawning and need to import models. One tower shoots enemies, but we still need ot add attacks to other towers and pair the first tower's attack animation to a script.
Team Members -- Billable Hours |  |  | t
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 5 | Risk | Importing models and animations is taking more time than expected and should probably be completed in the next week. Swarm spawning also needs to be added.
Peter Seely | AI Specialist/Enemy AI | 4
Nate Roylance | Chief Architect/Start Menu UI | 6
Joel Battaglia | Game Artist/Asset Creation | 5 | Issue
Joseph Scholl | Tower Expert/Tower Research | 4
Total |  | 24

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task