## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-02-26 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | Swarm spawning |  | 80% | Delayed |  | 2022-02-19
|  |  |  | New floor tiles |  | 99% | Possible Delays |  | 2022-02-26
|  |  |  | Attack code for 2 new tower models |  | 90% | Possible Delays |  | 2022-02-26
|  |  |  | Health bars for enemies |  | 0% | Possible Delays |  | 2022-03-12
|  |  |  | Flying enemy mapping |  | 100% | On Track |  | 2022-02-26
|  |  |  | Sound effects |  | 0% | Future Task |  | 2022-03-12
|  |  |  | Themed bgs |  | 0% | Future Task |  | 2022-03-12
|  |  |  | Player powers |  | 0% | Future Task |  | 2022-03-12
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Enemies taking damage. Enemy model and animation working. Tower shooting and damaging enemies and script is linked to particle system. Economy working and towers cannot be bought if funds are insufficient. Tower preview before placement. Particle effect on damaged enemies. Two towers are working and a third needs to be imported. |  |  | Everyone needs to push their github branches and get them merged together. Then we will have the new floor tiles completed and the two new tower models functioning. Everyone was busy this week so we didn't get started on health bars. |  |  | Swarm spawning and health bars are the two biggest tasks to be completed. They have both been delayed due to some unity issues that are mostly debugged now. Then, we can begin to add sound effects, themed backgrounds, and player powers.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 6 | Risk | Some team members are having issues with github and there was some progress that was overwritten that we had to redo. We will be more careful now with how we commit and push changes.
Peter Seely | AI Specialist/Enemy AI | 6.5
Nate Roylance | Chief Architect/Start Menu UI | 4
Joel Battaglia | Game Artist/Asset Creation | 4 | Issue
Joseph Scholl | Tower Expert/Tower Research | 5
Total |  | 25.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task