## Status Report
Project Name | Capture the Flag |  | Date |  | 2022-02-19 | Project Manager |  | Adam Johnson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Changed from a FPS to a tower defense game. It will be a simple, futuristic, tower defense game. The goal is to defend your base for as long as possible against swarms of enemy units by building turrets. |  |  |  | Swarm spawning |  | 40% | Delayed |  | 2022-02-19
|  |  |  | Glowing effects on enemies and turrets |  | 10% | On Track |  | 2022-02-26
|  |  |  | Attack code for 2 new tower models |  | 20% | On Track |  | 2022-02-26
|  |  |  | Health bars for enemies |  | 0% | On Track |  | 2022-02-26
|  |  |  | Flying enemy mapping |  | 0% | Future Task |  | 2022-02-26
|  |  |  | Sound effects |  | 0% | Future Task |  | 2022-02-26
|  |  |  | Themed bgs |  | 0% | Future Task |  | 2022-03-05
|  |  |  | Player powers |  | 0% | Future Task |  | 2022-03-05
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Enemies taking damage. Enemy model and animation working. Tower shooting and damaging enemies and script is linked to particle system. Economy working and towers cannot be bought if funds are insufficient. Tower preview before placement. Particle effect on damaged enemies. |  |  | Swarm spawning delayed due to a team member's unity issues. |  |  | Main task is to implement swarm spawning and waves. Health bars, glowing effects, and flying enemy mapping are also tasks for next week.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Adam Johnson | Project Manager/Environment | 5 | Risk
Peter Seely | AI Specialist/Enemy AI | 5
Nate Roylance | Chief Architect/Start Menu UI | 7
Joel Battaglia | Game Artist/Asset Creation | 4 | Issue | Unity issues that need to be debugged.
Joseph Scholl | Tower Expert/Tower Research | 3
Total |  | 24

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task